## Coronado_Methods
Method | Function | Corresponding_Shaikh_Tonak | Data_Requirements | Current_Status
Labor Value Calculations | V_vector(A, L) | Chapter 4 - Labor Values | A matrices, L vectors | Available in Coronado
Price-Value Analysis | H_mat(A), prices_prod() | Chapter 5 - Price-Value | A matrices, prices | Available in Coronado
Straight Index (SI) | Straight_index() | Chapter 5 - Price Deviations | Price curves | Available in Coronado
Eigenvalue Analysis | eigenvalue analysis | Economic Structure | A matrices | Available in Coronado
Multi-Level Aggregation | aggregation procedures | Industry Analysis | Multiple aggregation levels | Available in Coronado
Price Curves | price curve generation | Price Curves | Price-value data | Available in Coronado
Living/Dead Labor Ratios | HV calculations | Labor Analysis | Labor and value data | Available in Coronado
Power Law Analysis | distribution fitting | Economic Regularities | Eigenvalue data | Available in Coronado
Economic Structure Analysis | eigenvalue distributions | Structural Analysis | Matrix data | Available in Coronado
Time Series Analysis | annual time series | Historical Analysis | Time series data | Available in Coronado

## Integration_Roadmap
Phase | Task | Timeline | Priority
Phase 1 | Convert R functions to Python | Week 1-2 | HIGH
Phase 1 | Create data loading pipeline | Week 1-2 | HIGH
Phase 1 | Implement basic calculations | Week 2-3 | HIGH
Phase 1 | Test with 2017 data | Week 3 | HIGH
Phase 2 | Implement labor value calculations | Week 4-5 | HIGH
Phase 2 | Implement price-value analysis | Week 4-5 | HIGH
Phase 2 | Create Straight Index calculations | Week 5-6 | HIGH
Phase 2 | Generate price curves | Week 6 | MEDIUM
Phase 3 | Implement eigenvalue analysis | Week 7-8 | MEDIUM
Phase 3 | Create multi-level aggregation | Week 7-8 | MEDIUM
Phase 3 | Generate time series analysis | Week 8-9 | MEDIUM
Phase 3 | Create visualization tools | Week 9 | MEDIUM
Phase 4 | Validate against Coronado results | Week 10 | HIGH
Phase 4 | Integrate with existing code | Week 10-11 | HIGH
Phase 4 | Create comprehensive outputs | Week 11-12 | HIGH

## R_to_Python_Functions
R_Function | Python_Equivalent | Description | Complexity
V_vector(A,L) | def v_vector(A, L): | Labor value vector: V = L * (I - A)^(-1) | Medium
H_mat(A) | def h_matrix(A): | H matrix for price calculations | Medium
prices_prod(V, H, EE, x) | def prices_production(V, H, EE, x): | Prices of production calculation | High
Straight_index(prices, x) | def straight_index(prices, x): | Straight Index for price-value deviations | High
Z(A) | def z_matrix(A): | Convert A matrix to Z matrix | Low
A_2(Z) | def a_matrix(Z): | Convert Z matrix back to A matrix | Low
reducedz(mak, tt) | def reduce_matrix(mak, tt): | Matrix aggregation function | High
L_vector_Z(Z, Aver_wage) | def labor_vector_z(Z, avg_wage): | Labor vector from Z matrix | Medium
eigen() | np.linalg.eig() | Eigenvalue calculation | Low
solve() | np.linalg.solve() | Matrix inversion | Low

## Data_Integration
Data_Source | Format | Integration_Method | Priority
Coronado A Matrices | CSV files | Direct conversion | HIGH
Coronado L Vectors | CSV files | Direct conversion | HIGH
Coronado SI Results | CSV files | Use as validation | HIGH
BEA IO Tables 1997-2023 | Excel files | Process and convert | HIGH
BEA Historical Tables | Excel files | Process and convert | MEDIUM
BLS Employment Data | CSV files | Process and convert | MEDIUM
Current SHAIKHTONAK Results | CSV files | Merge with new results | HIGH
Book Tables | PDF tables | Target for replication | HIGH
Validation Data | Various | Cross-validation | HIGH

## Expected_Outcomes
Outcome | Description | Impact
Perfect Shaikh & Tonak Replication | Exact replication of book results | HIGH
Advanced Price-Value Analysis | Straight Index and price curves | HIGH
Comprehensive Time Series | 1997-2023 annual analysis | HIGH
Multi-Level Industry Analysis | 15, 71, and 389 sector levels | HIGH
Economic Structure Analysis | Eigenvalue and power law analysis | MEDIUM
Publication-Ready Results | Academic publication quality | HIGH
Interactive Dashboards | User-friendly analysis tools | MEDIUM
Methodological Innovation | Extensions beyond original book | HIGH